## Sheet1
Risk | Probability | Impact | Planning Strategy | Action
HW delay | H | H | Avoid/Mitigate | rent from local supplier
delay in development or in testing | L | H | Avoid | employ enough members
Hacking | L | H | Avoid | employ security engineers
Training is not enough or take much time | L | M | Transfer | transfer to client