## Sheet1
PBS
HW | SW | Process | Server | Mob App | Training
Laptop | java script | Users | PHP | offers and pormotions | java script
Mobile | python | admins | .NET | add and remove offers | python
Server | HTML | moderators | C# | create account | HTML
| SQL |  |  | subscribe for offers | SQL
WBS
Secure HW |  | Instal SW tools | Install tools for server creation | Design & develop App |  | Sechdule Trainings
Secure Laptops | select supplier, buy, test | Instal Angular JS | Instal PHPStorm | design module for subscribe | develop & test | schedule java script training
Secure mobile | select supplier, buy, test | Install python 3 | Install visual studio | design module for home page | develop & test | schedule python training
Secure Server |  | Install Notepad++ |  | design module for acc setting | develop & test | schedule HTML training
|  |  |  | design module for pormotions | develop & test | schedule SQL training
OBS
PM
Training Team Leader | Suppliers Manager | Development Team Leader | Testing Team Leader | Process writer
java script trainer | Supplier1 | developer1 | tester1
python trainer | Supplier2 | developer2 | tester2
HTML trainer |  | developer3 | tester3
SQL trainer