## Sheet1
Time | PV | EV | AC
0 | 0 | 0 | 0 | The project is over budget with 1500 Hrs
10 | 5000 | 5500 | 7000 | The project is not delayed, it's ahead by 500 Hrs -> 12.5 days (8 working/day)
20 | 10000